## 20241023020000
Id | Type | Region | Navigation | Location | Description | Towpath closed? | Start date | End date | Link
28758 | Navigation Closure | North West | Ribble Link | Lock No 4, Ashton on Ribble, Preston | The Rip Rap/Gabion baskets behind the flood weir at Lock 4 has been scoured out by flood water.The repair is to clear the debris, carry out repairs to the gabions and rip rap reinstatement, geotextile and topsoil/seeding. | No | 2024-09-30T08:00:00+01:00 | 2024-11-08T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28758-lock-no-4-ashton-on-ribble-preston
29084 | Navigation Restriction | North West | Weaver Navigation | Dutton Large Lock, Bartington | The works at this location have been delayed due to high river flows. Unfortunately, this has prevented us from carrying out the planned works in the original time frame. We are hopeful to start work on site on the 14 October 2024 with a completion date of the 19 December 2024. From the 28 October bookings will be required 2 days before, via the normal booking system. Whilst we are carrying out work at this lock there may be a short delay. Please follow instructions from the contractors on site. If you are after an urgent passage, please contact customer services on 03030 404040 and select the North West region. | No | 2024-10-14T08:00:00+01:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29084-dutton-large-lock-bartington
28749 | Navigation Closure | East Midlands | Leicester Line (Grand Union Canal) | Lock 35, Whetstone Lane Lock, Whetstone | A stoppage is required for top side & low side lock gate replacements and lock chamber wall brickwork. | Yes | 2024-10-28T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28749-lock-35-whetstone-lane-lock-whetstone
28160 | Navigation Closure | West Midlands | Shropshire Union Canal | Clare's Culvert 70, Adderley | A navigation closure is required for offside Culvert leak repair works | No | 2024-11-04T08:00:00+00:00 | 2024-12-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28160-clares-culvert-70-adderley
28162 | Navigation Closure | North West | Ribble Link | Lock 5, Lea, Preston | Removal of both of the rotten quoin boards and replace them with new oak quoin boards including fixings on the head gate. We will also repair the tail gate mitre by inserting hardwood into the mitre to stop the leak. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28162-lock-5-lea-preston
28164 | Navigation Closure | North West | Rochdale Canal | Lock 69, Newton Heath, Failsworth | A stoppage is required to replace the top & bottom lock gates. | No | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28164-lock-69-newton-heath-failsworth
28165 | Navigation Restriction | West Midlands | Grand Union Canal | Longhole Viaduct - High Speed 2 over the Grand Union Canal, near Ufton | A navigation restriction is required to construct a new viaduct over the Grand Union Canal for High Speed 2. Pontoons and construction plant will be in the navigation restricting the width. | No | 2024-11-04T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28165-longhole-viaduct-high-speed-2-over-the-grand-union-canal-near-ufton
28168 | Navigation Closure | North West | Shropshire Union Canal | Pipeline crossing next to Bridge 130, Mollington | Contractors working for Cadent gas have not been able to secure a road closure from the council for the original planned closure dates. Therefore they would like to revise them. The new closure dates are from the 4 November 2024 through to the 15 November 2024. The towpath will remain open. | No | 2024-11-04T08:00:00+00:00 | 2024-11-15T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28168-pipeline-crossing-next-to-bridge-130-mollington
28173 | Navigation Closure | North West | Leeds & Liverpool Canal | Service Crossings, attached to Rishton Bridge 108A | A stoppage is required to allow contractors to erect scaffolding and encapsulate pipes for abrasive blasting & Inspections they will also apply a 4-coat epoxy paint system. | No | 2024-11-04T08:00:00+00:00 | 2024-11-18T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28173-service-crossings-attached-to-rishton-bridge-108a
28181 | Navigation Closure | Yorkshire & North East | Bank Dole Cut | Pipe crossing adjacent to Trundles Lane Bridge, Knottingley | Scaffolding blocking waterway required for gas pipeline refurbishment | No | 2024-11-04T08:00:00+00:00 | 2024-11-22T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28181-pipe-crossing-adjacent-to-trundles-lane-bridge-knottingley
28188 | Navigation Closure | West Midlands | Shropshire Union Canal | Tyrley Lock 4, Market Drayton | A navigation and towpath closure are required for masonry repairs to the offside chamber wall, towpath side. | Yes | 2024-11-04T08:00:00+00:00 | 2024-11-29T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28188-tyrley-lock-4-market-drayton
28196 | Navigation Closure | London & South East | Grand Union Canal | HS2 Colne Valley Viaduct, 500m south of Moorhall Road, Denham | We have been advised that HS2 can now do this part of their construction works as a series of overnight closures. Therefore, the canal and towpath will no longer be closed to facilitate these works. | Yes | 2024-11-04T08:00:00+00:00 | 2024-08-28T14:00:00+01:00 | https://canalrivertrust.org.uk/notices/28196-hs2-colne-valley-viaduct-500m-south-of-moorhall-road-denham
28201 | Navigation Closure | West Midlands | Stourbridge Canal | Lock 6, Stourbridge | A navigation and towpath closure are required for top and bottom lock gate replacements. We will also be doing a full lock ladder rebuild, Lock chamber brickwork repairs and wingwall leak repairs. The whole flight of locks will be closed to eliminate the risk of flooding the site. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28201-lock-6-stourbridge
28210 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 77, of the Wigan Flight, Wigan | A stoppage is required for wash wall repairs. Approximately 5m needs rebuilding on the offside of the canal. | No | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28210-lock-77-of-the-wigan-flight-wigan
28211 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 51, Wootton Rivers | A stoppage is required to carry out repair and refurbishment of the top lock gates. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28211-lock-51-wootton-rivers
28723 | Navigation Closure | Wales & South West | Monmouthshire & Brecon Canal | Between Bridge 110 and Bridge 114, Llangattock | A stoppage is required to carry out leak investigation and clay repairs to canal bank at Llangattock. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T18:00:00+00:00 | https://canalrivertrust.org.uk/notices/28723-between-bridge-110-and-bridge-114-llangattock
28213 | Navigation Closure | London & South East | River Stort | Feakes Lock 7, Sawbridgeworth | A stoppage is required to carry out repair and refurbishment works to the top and bottom lock gates. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28213-feakes-lock-7-sawbridgeworth
28215 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 55, Crofton | A stoppage is required to carry out repair and refurbishment works to the top lock gates. We are closing a larger section of navigation as the work at lock 55, Crofton and lock 52, Heathy Close, Wootton Rivers, will be done in succession. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28215-lock-55-crofton
28216 | Navigation Closure | London & South East | Aylesbury Arm (Grand Union Canal) | Lock 12, Aylesbury | A stoppage is required to carry out replacement of the bottom gates, along with other repair works along the Aylesbury Arm. | No | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28216-lock-12-aylesbury
28732 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 60 Johnson's Hillock | A stoppage is required to carry out works to prevent leakage through the lock chamber walls and head forebay. | No | 2024-11-04T08:00:00+00:00 | 2024-11-15T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28732-lock-60-johnsons-hillock
28736 | Navigation Closure | North West | Rochdale Canal | Key Lane Lock 64, offside Landing, Middleton, Manchester. | A stoppage is required for the removal and repairs of the upstream lock landing and upstream wash wall. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28736-key-lane-lock-64-offside-landing-middleton-manchester
28737 | Navigation Closure | North West | Rochdale Canal | Lock 65 Alfred street, Failsworth (between Oldham and Manchester) | The works here are aimed at tackling the leakage into the lock from the bywash. The works that will take place will be a grout curtain placed adjacent to the bywash to stop water ingress into the lock. Grout will also be injected into the lock walls to fill any remaining voids. | No | 2024-11-04T08:00:00+00:00 | 2024-11-22T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28737-lock-65-alfred-street-failsworth-between-oldham-and-manchester
28237 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 52, Heathy Close, Wootton Rivers | A stoppage is required to carry out replacement of the bottom gates. We are closing a larger section of navigation as the work at lock 52, Heathy Close, Wootton Rivers, and lock 55, Crofton will be done in succession. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28237-lock-52-heathy-close-wootton-rivers
28750 | Navigation Closure | East Midlands | Grand Union Canal | Lock 3 Braunston (Braunston) | For water control reasons, we have had to widen the closure area for these planned works. The new closure area is from Lock 2 through to Lock 6, Top Lock. The closure dates remain the same; 4 November 2024 through to the 19 December 2024. Please note we will only be dewatering Lock 3, Braunston. | No | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28750-lock-3-braunston-braunston
28751 | Navigation Closure | West Midlands | Llangollen Canal | Lyneal Lane Bridge 51, Welshampton | Contractors working for the highway authority will be carrying out repairs to the highway bridge. The works will require a fixed pontoon, scaffolding and underwater repairs by diving. The towpath will be closed between the 04 November 2024 and the 08 November 2024, a diversion route will be signed. | Yes | 2024-11-04T08:00:00+00:00 | 2024-11-18T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28751-lyneal-lane-bridge-51-welshampton
28241 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 75 of the Wigan Flight, Wigan | A stoppage is required to rebuild the collapsed section of wash wall beneath the by-wash outlet to prevent further collapse. The collapsed masonry will be utilised to maintain the tone and grain of the existing wall to meet heritage standards. | No | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28241-lock-75-of-the-wigan-flight-wigan
28754 | Navigation Closure | North West | Llangollen Canal | Baddiley Lock 2, Wrenbury Heath | A stoppage is required for pointing of gaps in the chamber walls, reducing leaks in the bottom end mitre gates, and replacement of missing bricks and repairs to the spalled sections of the chamber wall. | No | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28754-baddiley-lock-2-wrenbury-heath
28243 | Navigation Closure | West Midlands | Oxford Canal | Napton Lock 11, Napton on the Hill | A navigation and towpath closure is required for leak repairs on the pound sidewall. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-13T17:00:00+00:00 | https://canalrivertrust.org.uk/notices/28243-napton-lock-11-napton-on-the-hill
28244 | Navigation Closure | London & South East | Oxford Canal | Middle Bridge 145 | Oxfordshire County Council no longer need this planned closure. Therefore, in reference to this notice, the navigation and towpath will be open at Middle Bridge 145 between the 4 November 2024 and the 17 November 2024. | Yes | 2024-11-04T08:00:00+00:00 | 2024-10-21T16:00:00+01:00 | https://canalrivertrust.org.uk/notices/28244-middle-bridge-145
29268 | Navigation Closure | West Midlands | Shropshire Union Canal | Between Bridge 24 & 25, High Onn, Shropshire Union Canal | Following a Safety review and feedback from customers, we have decided to delay this work and move it into the winter works programme. This is now a full navigational closure, the works will commence on 4 November 2024 and run through to 25 November 2024. | No | 2024-11-04T08:00:00+00:00 | 2024-11-25T17:00:00+00:00 | https://canalrivertrust.org.uk/notices/29268-between-bridge-24-25-high-onn-shropshire-union-canal
28248 | Navigation Closure | London & South East | Oxford Canal | Shipton Flood Gate, Shipton-on-Cherwell | A stoppage is required to carry out replacement of the flood gates, and repair to the offside wharf wall. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28248-shipton-flood-gate-shipton-on-cherwell
28252 | Navigation Closure | West Midlands | Staffordshire & Worcestershire Cnl | Bumble Hole Lock 22, Smestow | A navigation and towpath closure is required for top and bottom end lock gate replacement. We will also be doing a full lock ladder rebuild. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28252-bumble-hole-lock-22-smestow
28764 | Navigation Closure | North West | Weaver Navigation | Anderton Boat Lift, Northwitch | A stoppage is required to carry out main hydraulic cylinder modifications and annual maintenance to the boat lift. | No | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28764-anderton-boat-lift-northwitch
28766 | Navigation Closure | Wales & South West | Monmouthshire & Brecon Canal | Llanfoist Embankment, Llanfoist near Govilon | Boreholes are to be drilled at the back of the offside waterway wall to measure the ground water on the offside of the canal. The closure is needed due to offside road access not being possible therefore access will need to be gained along the towpath and then onto temporary a platform which will span the entire dewatered canal width. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28766-llanfoist-embankment-llanfoist-near-govilon
29085 | Navigation Closure | West Midlands | Coventry Canal | Lock 3 Coventry Canal | A navigation and towpath closure are required for top end and bottom end mitre gate replacements. We will also be repairing the lock ladder hoops. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29085-lock-3-coventry-canal
29089 | Navigation Closure | Yorkshire & North East | Leeds & Liverpool Canal | Lock 1, River Lock, Canal Wharf, Leeds | A navigation and towpath closure are required to enable repairs to be completed. Dewatering is required to identify the cause of the leak and to repair the downstream stop plank grooves as well as other repairs throughout the lock. Due to the nature of the repairs, temporary dams need to be constructed upstream and downstream of the lock. The footbridge will be closed for the duration of the works to ensure safety of pedestrians. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29089-lock-1-river-lock-canal-wharf-leeds
29093 | Navigation Closure | West Midlands | Oxford Canal | Bridge 130, Knotts Bridge | A navigation and towpath closure are required for contractors working on behalf of the Trust to enable demolition of this Bridge structure. Please note the towpath will remain closed when the navigation is reopened. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29093-bridge-130-knotts-bridge
29095 | Navigation Closure | Yorkshire & North East | Sheffield & South Yorkshire Nav | Doncaster Lock, Doncaster | A navigation and towpath closure are required to repair the detached downstream sluice and the damaged frame and upstream ground paddle. Works will also be carried out to rectify the severe boil on the upstream cills and replace 5 Lock ladders. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29095-doncaster-lock-doncaster
29096 | Navigation Closure | Yorkshire & North East | Sheffield & South Yorkshire Nav | Swinton Lock, Swinton, South Yorkshire. | A navigation and towpath closure are required to replace the bottom lock gates and cills. We will also be replacing 8 lock ladder tops. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29096-swinton-lock-swinton-south-yorkshire
29102 | Navigation Closure | London & South East | Hertford Union Canal | Accommodation Bridge 10, footbridge, Hackney Wick, London. | The planned stoppage for the removal of Accommodation Bridge 10 on the Hertford Union is still going ahead from the 04 November 2024 to the 08 November 2024 but the bridge will not be removed due to delays in getting a Section 38 agreement finalised for its replacement. Instead, the stoppage will be used to facilitate the safe demolition of a wall adjacent to the towpath and Lock 3, Bottom Lock. The towpath and navigation closure will ensure boats and towpath visitors are kept away from the site whilst the demolition takes place. | Yes | 2024-11-04T08:00:00+00:00 | 2024-11-08T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29102-accommodation-bridge-10-footbridge-hackney-wick-london
28143 | Navigation Closure | West Midlands | Dudley No 1 Canal | Delph Lock 6, Brierley Hill | A navigation and towpath stoppage are required for top and bottom end gate replacements. We will also be repairing the brickwork under the coping stones and anchor stone. The whole flight of locks will be closed to eliminate the risk of flooding the site. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28143-delph-lock-6-brierley-hill
28145 | Navigation Closure | North West | Shropshire Union Canal | Hack Green, Lock 1, Audlem | A stoppage is required for repair works to be done to the pointing & brickwork, lock ladder and Lock gate liner. | No | 2024-11-04T08:00:00+00:00 | 2024-12-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28145-hack-green-lock-1-audlem
28147 | Navigation Closure | West Midlands | Coventry Canal | Lock 11, Atherstone | A navigation and towpath stoppage are required for top end and bottom end mitre gate replacements. We will also be repairing the lock ladder hoops. | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28147-lock-11-atherstone
28149 | Navigation Closure | Yorkshire & North East | Selby Canal | A19 Burn Bridge 3, Brayton | A navigation and towpath stoppage are required for sandblasting, repair and repainting of bridge | Yes | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28149-a19-burn-bridge-3-brayton
28151 | Navigation Closure | Yorkshire & North East | Leeds & Liverpool Canal | Bank Newton, lock 37, 5th lock | A stoppage is required to allow Lock gate replacement and repair works. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28151-bank-newton-lock-37-5th-lock
28155 | Navigation Closure | Yorkshire & North East | Leeds & Liverpool Canal | Bank Newton, lock 41, Top lock | A stoppage is required for tail gate replacement and lock chamber repairs. | No | 2024-11-04T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28155-bank-newton-lock-41-top-lock
28156 | Navigation Closure | North West | Rochdale Canal | Lock 39, Timbercliffe | A stoppage is required for repairs to the top lock gates & cills. | No | 2024-11-04T08:00:00+00:00 | 2024-11-22T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28156-lock-39-timbercliffe
29180 | Navigation Closure | Yorkshire & North East | Rochdale Canal | Lock 8, Mayroyd | A Navigational closure to inspect and repair the boil on the tail gate. | No | 2024-11-04T08:00:00+00:00 | 2024-12-02T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29180-lock-8-mayroyd
28742 | Navigation Closure | Yorkshire & North East | Leeds & Liverpool Canal | Bridge 195 Booth's swing Bridge between Bingley and Silsden near Keighley. | Some of the steel structure on Booths swing bridge has deteriorated due to corrosion leading to the bridge being inoperable. The bridge has had to be locked off in the canal open position. This has led to the closure of a popular public right of way. Works are required to remove and replace corroded sections of the steel structure under the bridge. The pintel also needs removing, inspecting and potentially refurbishing. To safely carry out the works the bridge will have to be moved into the canal closed position and jacked up to be able to remove the sections/pintel and have the bridge fully supported on its bearing points for the duration of the works. Other options have been explored but due to the weight of the bridge and poor access to site for suitably sized plant this is the best option. | No | 2024-11-06T08:00:00+00:00 | 2024-11-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28742-bridge-195-booths-swing-bridge-between-bingley-and-silsden-near-keighley
28714 | Navigation Closure | West Midlands | Titford Canal | Tat Bank Bridge, Oldbury | A stoppage is required for repairs to the Highways bridge. Scaffolding and bridge encapsulating will be needed to complete these works. | Yes | 2024-11-11T08:00:00+00:00 | 2024-11-30T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28714-tat-bank-bridge-oldbury
28251 | Navigation Closure | West Midlands | Stourbridge Canal | Stourton Lock 3, Stourton | A navigation and towpath closure is required to replace the top end single and bottom end mitres on the lock gates. We will also be extending the lock ladder and replacing the hoops. | Yes | 2024-11-11T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28251-stourton-lock-3-stourton
29092 | Navigation Closure | East Midlands | Trent & Mersey Canal | Lock 1 Derwent Mouth, Shardlow | A navigation and towpath closure are required for repairs to leaking gates. We will also be doing lock ladders works and chamber brickworks. | Yes | 2024-11-11T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29092-lock-1-derwent-mouth-shardlow
29176 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 61 Johnson's Hillock | A navigational closure is required to refurbish Lock 61. Please note we also have closure notices for Locks 60 and 62. | No | 2024-11-11T08:00:00+00:00 | 2024-12-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29176-lock-61-johnsons-hillock
29177 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 62 Johnson's Hillock | A navigational closure is required to refurbish lock 62. Please note we also have closure notices for locks 60 and 61. | No | 2024-11-11T08:00:00+00:00 | 2024-12-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29177-lock-62-johnsons-hillock
28161 | Navigation Closure | North West | Rochdale Canal | Lock 41, Littleborough | A stoppage is required for leak repairs to quoin & cills. | No | 2024-11-18T08:00:00+00:00 | 2024-12-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28161-lock-41-littleborough
28744 | Navigation Closure | North West | Shropshire Union Canal | Sluice near Bridge 91, Marsh Lane, Nantwich (works on culvert 49 going on) | A stoppage is required due to localised dewatering of the canal to facilitate an underwater Inspection, desilting and refurbishment of the operational sluice. A fabric dam will be placed around the sluice so water can still pass. Unfortunately boats can not pass due to the fragility of the dam. | No | 2024-11-18T08:00:00+00:00 | 2024-11-29T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28744-sluice-near-bridge-91-marsh-lane-nantwich-works-on-culvert-49-going-on
28240 | Navigation Closure | North West | Glasson Branch (Lancaster Canal) | Lock 3, Near Upper Thurnham | A stoppage is required to isolate the by-wash weir on Lock 3 to enable missing masonry cobbles to be reset/replaced and re-pointed with lime mortar. | No | 2024-11-18T08:00:00+00:00 | 2024-11-29T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28240-lock-3-near-upper-thurnham
29178 | Navigation Closure | North West | Bugsworth Arm (Peak Forest Canal) | Bugsworth Basin Whaley Bridge | A navigational closure is required to rebuild the stone wash wall and reset the coping stones. As part of this work, we will be installing two fabric dams. | No | 2024-11-18T08:00:00+00:00 | 2024-11-29T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29178-bugsworth-basin-whaley-bridge
28245 | Navigation Closure | London & South East | Oxford Canal | Middle Bridge 145 | Oxfordshire County Council no longer need this planned closure. Therefore, with reference to this notice, the navigation will be open at Middle Bridge 145 between the 18 November 2024 and the 29 November 2024 | No | 2024-11-18T20:00:00+00:00 | 2024-10-21T06:00:00+01:00 | https://canalrivertrust.org.uk/notices/28245-middle-bridge-145
28175 | Navigation Closure | Yorkshire & North East | Rochdale Canal | Lock 17, near Todmorden | A stoppage is required to allow Lock gate leakage repairs and gate fender repair works. | No | 2024-11-25T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28175-lock-17-near-todmorden
28724 | Navigation Closure | West Midlands | Llangollen Canal | Springhill Bridge 41, Whitchurch | These works are no longer going ahead within this winter works programme; we are hopeful that they can be delivered next winter. This means the navigation and towpath, in reference to this notice, are now open at Springhill Bridge 41 from the 25 November 2024 to the 20 December 2024. | Yes | 2024-11-25T08:00:00+00:00 | 2024-10-21T08:00:00+01:00 | https://canalrivertrust.org.uk/notices/28724-springhill-bridge-41-whitchurch
28725 | Navigation Closure | Yorkshire & North East | Bank Dole Cut | Bank Dole Lock 5, located on the edge of Knottingley | A stoppage is required to stop the leak at the end of the lock island into the river and from the lock walls into the lock chamber.We will inject grout into the lock chamber walls to fill the voids and hopefully prevent any future leakage paths. | No | 2024-11-25T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28725-bank-dole-lock-5-located-on-the-edge-of-knottingley
28745 | Navigation Closure | North West | Shropshire Union Canal | Sluice 7, Moss Hall, by Bridge 80, Audlem | A stoppage is required due to localised dewatering of the canal to facilitate an underwater Inspection, desilting and refurbishment of the operational sluice. A fabric dam will be placed around the sluice so water can still pass. Unfortunately boats can not pass due to the fragility of the dam. | No | 2024-11-25T08:00:00+00:00 | 2024-12-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28745-sluice-7-moss-hall-by-bridge-80-audlem
28238 | Navigation Closure | West Midlands | Llangollen Canal | Hassells Bridge 33, Whitchurch | A navigation and towpath closure is required to repair the brickwork to the offside and towpath approaches. We will also be doing void repairs under the coping stones and installing new fenders. | Yes | 2024-11-25T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28238-hassells-bridge-33-whitchurch
29088 | Navigation Closure | North West | Leeds & Liverpool Canal | Yorkshire Street Aqueduct, Burnley | A navigation and towpath closure are required to enable a comprehensive inspection of the canal wash walls and bed. This will involve the installation of two fabric dams, one at Finsley Gate and one at Yorkshire Street aqueduct, followed by a fish rescue and then de-watering. | Yes | 2024-11-25T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29088-yorkshire-street-aqueduct-burnley
28158 | Navigation Closure | Yorkshire & North East | Rochdale Canal | Bridge 25, Shaw Wood Bridge, Todmorden | A stoppage is required for refurbishment of the gas main attached to Shaw Wood bridge. This will require scaffolding which will block the navigation | No | 2024-11-25T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28158-bridge-25-shaw-wood-bridge-todmorden
28159 | Navigation Closure | North West | Rochdale Canal | Lock 40 Punchbowl, Littleborough | A stoppage is required for repairs to the top & bottom lock gates. We will also be doing repairs to the Lock ladders. | No | 2024-11-25T08:00:00+00:00 | 2024-12-19T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28159-lock-40-punchbowl-littleborough
28166 | Navigation Closure | West Midlands | Oxford Canal | High Speed 2 viaduct over Oxford Canal Wormleighton | A navigation and towpath stoppage are required for construction of a new viaduct for High Speed 2. A towpath diversion will be in place. | Yes | 2024-12-02T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28166-high-speed-2-viaduct-over-oxford-canal-wormleighton
28759 | Navigation Closure | West Midlands | Shropshire Union Canal | Sluice 9, Audlem Flood Valve, Above Audlem Lock 1 | A stoppage is required due to localised dewatering of the canal to facilitate an underwater Inspection, desilting and refurbishment of the operational sluice. A fabric dam will be placed around the sluice so water can still pass. Unfortunately boats can not pass due to the fragility of the dam. | No | 2024-12-02T08:00:00+00:00 | 2024-12-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28759-sluice-9-audlem-flood-valve-above-audlem-lock-1-
28253 | Navigation Closure | West Midlands | Staffordshire & Worcestershire Cnl | Park Gate Lock 40, Penkridge | A navigation and towpath closure is required to reset ground paddle stand on the lock. | Yes | 2024-12-09T08:00:00+00:00 | 2024-12-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28253-park-gate-lock-40-penkridge
28191 | Navigation Closure | Wales & South West | Monmouthshire & Brecon Canal | Brecon Basin, Brecon | A stoppage is required to repair the copings in Brecon Basin. | No | 2025-01-02T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28191-brecon-basin-brecon
28712 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Culvert 14, between lock 20 east and lock 21 east, Slaithwaite | A stoppage is required due to de-watering of the canal between Lock 20 East and Lock 21 East to enable replacement of the culvert beneath the canal bed and towpath. | No | 2025-01-02T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28712-culvert-14-between-lock-20-east-and-lock-21-east-slaithwaite
28208 | Navigation Closure | West Midlands | New Mainline, Spon Lane Locks | Bromford Junction, Oldbury | We are pleased to advise that Network Rail are now able to undertake these works without closing the navigation and towpath, therefore they will now be open for the duration of the project. | Yes | 2025-01-02T08:00:00+00:00 | 2024-09-13T00:00:00+01:00 | https://canalrivertrust.org.uk/notices/28208-bromford-junction-oldbury
28721 | Navigation Closure | Wales & South West | Monmouthshire & Brecon Canal | Between Bridge 76 and Bridge 88, Llanover | A stoppage is required for Investigation and clay repair to the canal bank. We will also be doing repairs to culvert 48. | No | 2025-01-02T08:00:00+00:00 | 2025-03-14T18:00:00+00:00 | https://canalrivertrust.org.uk/notices/28721-between-bridge-76-and-bridge-88-llanover
28212 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 91, Colthrop | A stoppage is required to carry out repair and refurbishment works to the top and bottom lock gates, as well as repairs to the lock chamber. | No | 2025-01-02T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28212-lock-91-colthrop
28217 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 33, Caen Hill Flight | A stoppage is required to carry out replacement of the bottom lock gates, along with other packages of work along the flight. Locks 33 and 40 will be done in succession. The whole flight of locks will be closed to eliminate the risk of flooding the site. | No | 2025-01-02T08:00:00+00:00 | 2025-03-13T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28217-lock-33-caen-hill-flight
28218 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 40, Caen Hill Flight | A stoppage is required to carry out replacement of the bottom lock gates. Locks 33 and 40 will be done in succession. The whole flight of locks will be closed to eliminate the risk of flooding the site. | No | 2025-01-02T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28218-lock-40-caen-hill-flight
28752 | Navigation Closure | North West | Llangollen Canal | Bache House Bridge 2, Nantwich | This project covers the restoration of the wash wall back to its original condition. Due to a failure in the wash wall, one of the copping stones fell into the canal causing the remaining ones to lean in and parts of the towpath to wash away. We will be rebuilding the wash wall and replacing the copping stones. | Yes | 2025-01-02T08:00:00+00:00 | 2025-03-01T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28752-bache-house-bridge-2-nantwich
29082 | Navigation Restriction | North West | Weaver Navigation | Sutton swingbridge, Frodsham | A navigational restriction is required for replacement of key equipment to ensure reliable and safe operation of the swing bridge. This air draft restriction will only affect craft that are too large to fit in the Anderton boat lift. | No | 2025-01-02T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29082-sutton-swingbridge-frodsham
28163 | Navigation Closure | West Midlands | Oxford Canal | High Speed 2 Viaduct over Oxford Canal Wormleighton | A navigation and towpath stoppage are required for construction of a new railway viaduct over the Oxford Canal for High Speed 2. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-06T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28163-high-speed-2-viaduct-over-oxford-canal-wormleighton
28167 | Navigation Closure | North West | Huddersfield Narrow Canal | Offside canal embankment protection work. Nearest structure is Bridge 71 Wool Road. Diggle | A stoppage is required for offside embankment wash wall repairs. | No | 2025-01-06T08:00:00+00:00 | 2025-01-24T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28167-offside-canal-embankment-protection-work-nearest-structure-is-bridge-71-wool-road-diggle
28169 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Lock 1 East, Stanley Dawson Lock, Huddersfield | A stoppage is required to repair the leaking paddles in the lock chamber | No | 2025-01-06T08:00:00+00:00 | 2025-01-24T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28169-lock-1-east-stanley-dawson-lock-huddersfield
28170 | Navigation Closure | North West | Macclesfield Canal | Red Bull Aqueduct, Kidsgrove | A stoppage is required to carry out brickwork repairs to try and stop leakage onto road below. | No | 2025-01-06T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28170-red-bull-aqueduct-kidsgrove
28172 | Navigation Closure | North West | Huddersfield Narrow Canal | Service Crossings, attached to Bridge 87, Manchester Road Bridge | A stoppage is required to allow contractors to erect scaffolding and encapsulate pipes for abrasive blasting & Inspections they will also apply a 4-coat epoxy paint system. | No | 2025-01-06T08:00:00+00:00 | 2025-01-20T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28172-service-crossings-attached-to-bridge-87-manchester-road-bridge
28176 | Navigation Closure | West Midlands | Dudley No 2 Canal | Wright's bridge, Blackheath | A navigation and towpath stoppage are required for a full bridge replacement. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28176-wrights-bridge-blackheath
28186 | Navigation Closure | Yorkshire & North East | Huddersfield Broad Canal | Red Doles Lock 9, Huddersfield | A stoppage is required to replace the downstream Lock gates and cills, replace a broken top ground paddle and re-bed the Lock copings and re-point the Lock walls. | No | 2025-01-06T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28186-red-doles-lock-9-huddersfield
28187 | Navigation Closure | Yorkshire & North East | Sheffield & Tinsley Canal | Tinsley Lock 12, Sheffield. | A stoppage is required to replace both upstream and downstream lock gates, we will also be replacing the lock ladders and doing off-side chamber wall brickwork repairs. | No | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28187-tinsley-lock-12-sheffield
28190 | Navigation Closure | Yorkshire & North East | Chesterfield Canal | Worksop town Lock approach wall, Bassetlaw, Worksop | A navigation and towpath closure are required to install new foundations & rebuild the approach wall on the towpath side of the canal. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28190-worksop-town-lock-approach-wall-bassetlaw-worksop
28194 | Navigation Closure | West Midlands | Trent & Mersey Canal | Shadehouse Lock 19, Fradley | A navigation and towpath stoppage are required for bottom end mitre gate replacements and Lock ladder hoops and associated brickwork repairs. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28194-shadehouse-lock-19-fradley
28195 | Navigation Restriction | East Midlands | River Trent | Mill Bridge 20, Access bridge to Newark Repair Yard, Newark | A navigation restriction and towpath closure are required for the Installation of new handrails on the bridge. Scaffolding is required and will hang down below the bridge reducing the air draft to 3m at normal summer levels rather than 4m. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28195-mill-bridge-20-access-bridge-to-newark-repair-yard-newark
28710 | Navigation Closure | West Midlands | Dudley No 2 Canal | Smith's bridge, Blackheath | A stoppage is required for minor works to improve the beam connections on Smith's Bridge. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28710-smiths-bridge-blackheath
28199 | Navigation Closure | West Midlands | Caldon Canal | Sluice 6, between bridges 38 & 39, Denford | These works are no longer going ahead within this winter works programme; we are hopeful that they can be delivered in 2026 via a 3rd party funder. This means the navigation and towpath, in reference to this notice, are now open between bridge 38 and 39 from the 6 January 2025 to 24 January 2025. | Yes | 2025-01-06T08:00:00+00:00 | 2024-10-21T08:00:00+01:00 | https://canalrivertrust.org.uk/notices/28199-sluice-6-between-bridges-38-39-denford
28206 | Navigation Closure | London & South East | Grand Union Canal | Bridge 108, Chelmscote, near Stoke Hammond | A navigation and towpath closure are required to carry out repairs to the waterway wall and towpath. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28206-bridge-108-chelmscote-near-stoke-hammond
28728 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Lock 5 East, Paddock Foot Lock. | The works here are aimed at preventing further leakage from the lock chamber into the River Colne.We will inject grout into the lock chamber walls to fill the voids. This will prevent the water leaking out of the lock chamber. | Yes | 2025-01-06T08:00:00+00:00 | 2025-01-24T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28728-lock-5-east-paddock-foot-lock
28729 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Lock 33 East, near Marsden | The works here are aimed at stopping leakage from the lock onto the towpath. This is leaking onto the cobbled slope down to below the bridge downstream. This makes the surface very slippery. We will inject grout into the lock chamber walls and quadrants. This will fill any voids and block any leakage paths preventing water leaking onto the towpath. | Yes | 2025-01-06T08:00:00+00:00 | 2025-01-24T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28729-lock-33-east-near-marsden
28730 | Navigation Closure | North West | Huddersfield Narrow Canal | Lock 4 West, Stalybridge | A stoppage is required to carry out head and tail lock gate replacements | No | 2025-01-06T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28730-lock-4-west-stalybridge
28731 | Navigation Closure | North West | Lancaster Canal | Culvert 59, near Blind Lane Bridge 115, Hest Bank | A stoppage is required for relining works on culvert 59.The work involves placing fabric dams to isolate the section of canal where the Culvert and bed valve is located.The clay bed will need excavating and replacing with new to stop the current leaks coming through the culvert. | No | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28731-culvert-59-near-blind-lane-bridge-115-hest-bank
28741 | Navigation Closure | Yorkshire & North East | Aire & Calder Navigation Main Line | Ferrybridge lock flood gates, in Ferrybridge | Replacement of time worn flood gates within the lock structure. New oak flood gates will be fitted on site. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28741-ferrybridge-lock-flood-gates-in-ferrybridge
28235 | Navigation Closure | London & South East | Grand Union Canal | Lock 65, Apsley, Near Hemel Hempstead | A stoppage is required to carry out replacement of the top lock gates. | No | 2025-01-06T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28235-lock-65-apsley-near-hemel-hempstead
28755 | Navigation Closure | London & South East | Oxford Canal | Lock 29, Banbury | A stoppage is required to carry out replacement of the top gate.We will also be doing balance beam and coping stone repairs. | No | 2025-01-06T08:00:00+00:00 | 2025-01-24T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28755-lock-29-banbury
28760 | Navigation Closure | West Midlands | Trent & Mersey Canal | Star Lock 27, Stone | A stoppage is required to for lock landing repairs. The towpath will be closed from the local scouts club HQ to Lock 27, star Lock, below the visitor moorings. | Yes | 2025-01-06T08:00:00+00:00 | 2025-01-31T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28760-star-lock-27-stone
28249 | Navigation Closure | London & South East | Regent's Canal | Lock 7, Actons Lock, Regents Row | The repair works to Lock 7, Actons Lock, are no longer going ahead. We have reprioritised the resource to lock 65, Aspley, on the Grand Union Canal. This means, with reference to this notice, Lock 7 will now be open between the 6 January 2025 and the 7 February 2025. | No | 2025-01-06T08:00:00+00:00 | 2024-10-21T08:00:00+01:00 | https://canalrivertrust.org.uk/notices/28249-lock-7-actons-lock-regents-row
28250 | Navigation Closure | Wales & South West | River Severn Navigation | Lock 2, Gloucester Lock, The Docks, Gloucester | A navigation and towpath closure is required to dewater Gloucester Lock to carry out inspections, repairs and improvements to water tightness. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28250-lock-2-gloucester-lock-the-docks-gloucester
28765 | Navigation Closure | Wales & South West | Monmouthshire & Brecon Canal | Llanfoist Embankment, Llanfoist near Govilon | Boreholes are to be drilled at the back of the offside waterway wall to measure the ground water on the offside of the canal. The closure is needed due to offside road access not being possible therefore access will need to be gained along the towpath and then onto temporary a platform which will span the entire dewatered canal width. In addition to this we will also be installing 2 sets of safety gates which will require localised dewatering and construction plant within the canal corridor. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28765-llanfoist-embankment-llanfoist-near-govilon
28254 | Navigation Closure | West Midlands | Trent & Mersey Canal | Woodend Lock 20, Fradley | A navigation and towpath closure is required to reline the top lock gate and replace the heads and heels on the bottom lock gate. We will also be doing a full lock ladder rebuild. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28254-woodend-lock-20-fradley
28255 | Navigation Closure | West Midlands | Worcester & Birmingham Canal. | Lock 2 Diglis, Worcester | A navigation and towpath closure is required for top lock gate replacement. We will also be doing a handrail bar spacing review | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28255-lock-2-diglis-worcester
28256 | Navigation Closure | West Midlands | Worcester & Birmingham Canal. | Gregorys Mill Lock 5, Worcester | A navigation and towpath closure is required for bottom lock gate replacements. We will also be doing a full lock ladder rebuild. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28256-gregorys-mill-lock-5-worcester
29083 | Navigation Closure | West Midlands | Llangollen Canal | Pontcysyllte Aqueduct, Trevor | A navigation and towpath closure are required for follow on works from the dewater and inspections we did last year. These works will include fender replacement, rivet replacement and paint defects. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29083-pontcysyllte-aqueduct-trevor
29091 | Navigation Closure | London & South East | Grand Union Canal | Culvert 164, Abbots Langley | A navigation closure is required for culvert Relining works. We will also reinstate the towpath and do some tree removal works. Please slow down when approaching and proceed with caution. The towpath will be closed but a temporary walkway will be in place. | No | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29091-culvert-164-abbots-langley
29094 | Navigation Closure | London & South East | Slough Arm (Grand Union Canal) | Reeds Bridge 2, Iver | A navigation and towpath closure are required to allow a new footbridge to be constructed over the canal. This will replace the one that was previously removed. This new bridge will restore the Right of Way over the canal. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29094-reeds-bridge-2-iver
29097 | Navigation Closure | West Midlands | Old Main Line | Lock 13, Wolverhampton | A navigation and towpath closure are required for top and bottom gate replacements, full lock ladder rebuild, and brickwork repairs. | Yes | 2025-01-06T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29097-lock-13-wolverhampton
28141 | Navigation Closure | North West | Macclesfield Canal | Bosley lock 10, near Bosley | A stoppage is required to replace the liners on the top and bottom gates to stop leakage. | No | 2025-01-06T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28141-bosley-lock-10-near-bosley
28144 | Navigation Closure | North West | Rufford Branch (L&L Canal) | Downstream of Lock 2 Rufford | A stoppage is required to rebuild the collapsed section of wash wall downstream of lock 2 on the towpath side. | No | 2025-01-06T08:00:00+00:00 | 2025-01-24T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28144-downstream-of-lock-2-rufford
28153 | Navigation Closure | West Midlands | Old Main Line | Lock 2, Wolverhampton | A stoppage is required for bottom lock gate replacements. We will also be doing a full lock ladder rebuild. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28153-lock-2-wolverhampton
28157 | Navigation Closure | West Midlands | Grand Union Canal | Lock 40 on the Hatton Flight, Hatton | A navigation and towpath stoppage are required for top and bottom lock gate replacements. We will also be doing a full lock ladder rebuild. The whole flight of locks will be closed to eliminate the risk of flooding the site. | Yes | 2025-01-06T08:00:00+00:00 | 2025-02-28T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28157-lock-40-on-the-hatton-flight-hatton
28189 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Wash wall repair at Tunnel End bridge 61, Marsden | A navigation and towpath stoppage are required for wash wall repairs near to bridge 61 Tunnel End, Marsden | Yes | 2025-01-13T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28189-wash-wall-repair-at-tunnel-end-bridge-61-marsden
28202 | Navigation Closure | East Midlands | Grand Union Canal | Lock 13, Long Buckby Wharf, Whilton, Daventry | A navigation and towpath stoppage are required for top side & low side lock gate replacements. We will also be doing lock chamber brickwork & ground paddle works. This work will run alongside the closure at Lock 12. | Yes | 2025-01-13T08:00:00+00:00 | 2025-03-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28202-lock-13-long-buckby-wharf-whilton-daventry
28203 | Navigation Closure | East Midlands | Grand Union Canal | Lock 12, Long Buckby Wharf, Whilton, Daventry | A navigation and towpath closure are required for topside lock gate replacement. We will also be doing lock chamber brickwork & paddle works. This work will run alongside the closure at lock 13. | Yes | 2025-01-13T08:00:00+00:00 | 2025-03-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28203-lock-12-long-buckby-wharf-whilton-daventry
28204 | Navigation Closure | East Midlands | River Soar | Lock 45, Birstall Lock, Birstall | A navigation and towpath closure are required for top side & low side lock gate replacement works. We will also be doing repairs to the lock floor & lock chamber wall brickwork. This work will run alongside the closure at Turnover Bridge 15. | Yes | 2025-01-13T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28204-lock-45-birstall-lock-birstall
28205 | Navigation Closure | East Midlands | River Soar | Turnover Bridge 15, Birstall, | A navigation and towpath stoppage are required to repair brickwork on the towpath side abutment. This work will run alongside the closure at Lock 45, Birstall. | Yes | 2025-01-13T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28205-turnover-bridge-15-birstall-
28233 | Navigation Closure | London & South East | Grand Union Canal | Lock 28, Grove Lock Marina, Leighton Buzzard | A stoppage is required to carry out replacement of the top and bottom lock gates. | No | 2025-01-13T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28233-lock-28-grove-lock-marina-leighton-buzzard
28762 | Navigation Closure | London & South East | Waterworks River | Bridgewater Road Bridge, Stratford Marsh | A Temporary bridge structure will be installed downstream of Bridgewater Road Bridge to accommodate these works. | Yes | 2025-01-13T08:00:00+00:00 | 2025-01-17T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28762-bridgewater-road-bridge-stratford-marsh
29107 | Navigation Closure | North West | Liverpool Link | Brunswick Dock, Liverpool | Additional work has been identified at the site and this has been coordinated in conjunction with the planned stoppage. Works are required to refurbish the river entrance lift bridge which is adjacent to the lock. The bridge will be lifted out, however, some of the work requires access into the lock. The additional work will extend the original dates by 3 weeks but will mitigate the requirement for an additional stoppage and minimise the disruption to our customers. | Yes | 2025-01-13T08:00:00+00:00 | 2025-03-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29107-brunswick-dock-liverpool
29174 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 83, of the Wigan Flight, Wigan | A navigational closure is required to refurbish Lock 83. | No | 2025-01-13T08:00:00+00:00 | 2025-02-03T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29174-lock-83-of-the-wigan-flight-wigan
28183 | Navigation Closure | Yorkshire & North East | Huddersfield Broad Canal | Railway Bridge 2, next to Colne Bridge Lock 2 | A navigation and towpath stoppage are required to allow Third Party Contractors working on behalf of Network Rail to refurbish and replace the bridge. This closure is to enable soil nailing to be undertaken to the bridge abutments. A pontoon crash deck is required over the canal to prevent debris falling into the watercourse or onto public on the towpath. | Yes | 2025-01-16T08:00:00+00:00 | 2025-03-04T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28183-railway-bridge-2-next-to-colne-bridge-lock-2
28174 | Navigation Closure | North West | Peak Forest Canal | Service Crossings, attached to under side of Bridge 2, Dog Lane Bridge, Dukinfield | A stoppage is required to allow contractors working for Cadent gas, to erect scaffolding and encapsulate pipes for abrasive blasting & Inspections they will also apply a 4-coat epoxy paint system. | No | 2025-01-20T08:00:00+00:00 | 2025-02-03T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28174-service-crossings-attached-to-under-side-of-bridge-2-dog-lane-bridge-dukinfield
28720 | Navigation Closure | North West | Macclesfield Canal | Sluice 8, Bollington near Clarence Mill Footbridge 26A | A stoppage is required due to localised dewatering of the canal to facilitate an underwater Inspection, desilting and refurbishment of the operational sluice. A fabric dam will be placed around the sluice so water can still pass. Unfortunately boats can not pass due to the fragility of the dam. | No | 2025-01-20T08:00:00+00:00 | 2025-01-31T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28720-sluice-8-bollington-near-clarence-mill-footbridge-26a
28154 | Navigation Closure | North West | Huddersfield Narrow Canal | Lock 22 West, Uppermill | A stoppage is required for repairs to the approach wall downstream of lock 22, towpath side. The watered section below the lock will be lowered to uncover the collapsed foundation of the approach wall. | No | 2025-01-20T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28154-lock-22-west-uppermill
28713 | Navigation Closure | West Midlands | Wyrley & Essington Canal | New road bridge to be constructed north of Yorks Bridge, Pelsall Common, Walsall. | A stoppage is required to safely install a new bridge deck along with enabling works which will block the navigation during the works due to Health & Safety reasons. | Yes | 2025-01-27T08:00:00+00:00 | 2025-02-02T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28713-new-road-bridge-to-be-constructed-north-of-yorks-bridge-pelsall-common-walsall
28207 | Navigation Closure | West Midlands | Caldon Canal | Hazelhurst Lock 10, Denford (Top Lock) | A navigation and towpath closure are required for ground paddle leak repairs. | Yes | 2025-01-27T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28207-hazelhurst-lock-10-denford-top-lock
28733 | Navigation Closure | North West | Macclesfield Canal | Sluice 10, Near Higherfold Bridge 33, Higher Hurdsfield | A stoppage is required due to localised dewatering of the canal to facilitate an underwater Inspection, desilting and refurbishment of the operational sluice. A fabric dam will be placed around the sluice so water can still pass. Unfortunately boats can not pass due to the fragility of the dam. | No | 2025-01-27T08:00:00+00:00 | 2025-02-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28733-sluice-10-near-higherfold-bridge-33-higher-hurdsfield
28242 | Navigation Closure | West Midlands | Montgomery Canal | Graham Palmer Lock, Lower Frankton | A navigation and towpath closure is required for top and bottom end lock gate replacements. We will also be repairing the coping stones. | Yes | 2025-01-27T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28242-graham-palmer-lock-lower-frankton
29086 | Navigation Closure | West Midlands | Montgomery Canal | Frankton Lock 4 | A stoppage is required for grouting the lock chamber walls. | No | 2025-01-27T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29086-frankton-lock-4
28738 | Navigation Closure | London & South East | Regent's Canal | 100m east of Bridge 31, Oblique Bridge, near St Pancras | A stoppage is required as part of the pedestrian access improvement works in relation to the redevelopment of the 6 St Pancras Way site. A new footbridge is being installed to connect public realm areas at 102 Camley Street and Granary Street. The bridge will be installed in three stages over a two week period. Following completion of the abutments to either side of the channel outside of the stoppage period, two approach ramps will be lifted into place where they will temporarily be cantilevered over the canal. The central span will then be lowered into place and secured to complete the deck. The three stages of installation will require navigation closure for the safety of canal users. This is the first of the 3 weekend closures. | Yes | 2025-02-01T08:00:00+00:00 | 2025-02-02T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28738-100m-east-of-bridge-31-oblique-bridge-near-st-pancras
28178 | Navigation Closure | Yorkshire & North East | Huddersfield Broad Canal | Lock 4, Longlands, Deighton, Huddersfield | A stoppage is required to investigate and repair the leaks to both the upstream and downstream lock gates and cills and replace the fenders on the downstream gates. | No | 2025-02-03T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28178-lock-4-longlands-deighton-huddersfield
28198 | Navigation Closure | London & South East | Grand Union Canal | Colne Valley Viaduct, High Speed 2, south of Moorhall Road, Denham | A stoppage is required for construction of the High Speed 2 railway viaduct over the Grand Union Canal. | Yes | 2025-02-03T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28198-colne-valley-viaduct-high-speed-2-south-of-moorhall-road-denham
28200 | Navigation Closure | West Midlands | Caldon Canal | Hazelhurst Lock 11 (Middle Lock), Denford | A navigation and towpath stoppage are required for top and bottom gate repairs and ground paddle leak repairs. | Yes | 2025-02-03T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28200-hazelhurst-lock-11-middle-lock-denford
28209 | Navigation Closure | North West | Trent & Mersey Canal | Lock 57, Hassall Green | A stoppage is required for replacement of the bottom lock gates. We will also fit new liners to the top gate and cill to prevent further leakage. | No | 2025-02-03T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28209-lock-57-hassall-green
28734 | Navigation Closure | North West | Macclesfield Canal | Sluice 12, Gurnett Aqueduct, Macclesfield | A stoppage is required due to localised dewatering of the canal to facilitate an underwater Inspection, desilting and refurbishment of the operational sluice. A fabric dam will be placed around the sluice so water can still pass. Unfortunately boats can not pass due to the fragility of the dam. | No | 2025-02-03T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28734-sluice-12-gurnett-aqueduct-macclesfield
29087 | Navigation Closure | London & South East | Grand Union Canal | Cassio Bridge near lock 78 | A stoppage is required for grouting the lock chamber wall. | No | 2025-02-03T08:00:00+00:00 | 2025-02-28T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29087-cassio-bridge-near-lock-78
28740 | Navigation Closure | London & South East | Regent's Canal | 100m east of Bridge 31, Oblique Bridge, near St Pancras | A stoppage is required as part of the pedestrian access improvement works in relation to the redevelopment of the 6 St Pancras Way site. A new footbridge is being installed to connect public realm areas at 102 Camley Street and Granary Street. The bridge will be installed in three stages over a two week period. Following completion of the abutments to either side of the channel outside of the stoppage period, two approach ramps will be lifted into place where they will temporarily be cantilevered over the canal. The central span will then be lowered into place and secured to complete the deck. The three stages of installation will require navigation closure for the safety of canal users. This is the second of the 3 weekend closures. | Yes | 2025-02-08T08:00:00+00:00 | 2025-02-09T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28740-100m-east-of-bridge-31-oblique-bridge-near-st-pancras
28179 | Navigation Closure | Yorkshire & North East | Huddersfield Broad Canal | Lock 5 Turnpike, Huddersfield | A stoppage is required to replace the life expired downstream lock gates, replace the lock ladder tops and re-point the lock walls. | No | 2025-02-10T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28179-lock-5-turnpike-huddersfield
28735 | Navigation Closure | North West | Peak Forest Canal | Sluice 1, Near Dog Lane Bridge 2, Dukinfield | A stoppage is required due to localised dewatering of the canal to facilitate an underwater Inspection, desilting and refurbishment of the operational sluice. A fabric dam will be placed around the sluice so water can still pass. Unfortunately boats can not pass due to the fragility of the dam. | No | 2025-02-10T08:00:00+00:00 | 2025-02-21T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28735-sluice-1-near-dog-lane-bridge-2-dukinfield
28236 | Navigation Closure | London & South East | Grand Union Canal | Lock 89, Cowley Lock, Cowley | A stoppage is required to carry out replacement of the top and bottom lock gates. | No | 2025-02-10T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28236-lock-89-cowley-lock-cowley
28756 | Navigation Closure | London & South East | Oxford Canal | Bridge 181, Scrooby's Lift Bridge, Kings Sutton | A stoppage is required to carry out repairs to the bridge, as well as the waterway wall under the bridge. | No | 2025-02-10T08:00:00+00:00 | 2025-03-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28756-bridge-181-scroobys-lift-bridge-kings-sutton
28761 | Navigation Closure | West Midlands | Walsall Canal | Lock 3, Ryders Green, Near West Bromwich | A stoppage is required for a Bywash channel rebuild. | Yes | 2025-02-10T08:00:00+00:00 | 2025-02-28T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28761-lock-3-ryders-green-near-west-bromwich
29103 | Navigation Closure | London & South East | Hertford Union Canal | Accommodation Bridge 10, Footbridge, Hackney Wick, London. | To improve pedestrian and cycle infrastructure across the Hertford Union Canal the existing footbridge at the junction between the Herford Union and River Lea is being replaced with a higher capacity structure. These works will require the towpath and navigation be closed for a short period so that the new bridge can be lifted into place safely. | Yes | 2025-02-10T08:00:00+00:00 | 2025-02-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29103-accommodation-bridge-10-footbridge-hackney-wick-london
28142 | Navigation Closure | North West | Macclesfield Canal | Bosley Lock 6, Bosley | A stoppage is required to repair the bottom lock gate by replacing both gate and Cill liners. | No | 2025-02-10T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28142-bosley-lock-6-bosley
29173 | Navigation Closure | West Midlands | Caldon Canal | Bank protection works, Etruria | A navigation and towpath closure is required to repair a 3 metre section of failing wash wall with associated towpath repairs. | Yes | 2025-02-10T08:00:00+00:00 | 2025-03-07T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29173-bank-protection-works-etruria
28150 | Navigation Closure | North West | Huddersfield Narrow Canal | Lock 2 West, Stalybridge | A stoppage is required to replace the head gate with a new gate. We will also be doing repairs to the tail gates and masonry repairs to the approach walls to the lock chamber. | No | 2025-02-10T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28150-lock-2-west-stalybridge
29175 | Navigation Closure | North West | Leeds & Liverpool Canal | Lock 73, of the Wigan Flight, Wigan | A navigational closure is required to refurbish Lock 73 and investigate the boil under the floor on the tail gate. | No | 2025-02-10T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29175-lock-73-of-the-wigan-flight-wigan
28743 | Navigation Closure | London & South East | Regent's Canal | 100m east of Bridge 31, Oblique Bridge, near St Pancras | A stoppage is required as part of the pedestrian access improvement works in relation to the redevelopment of the 6 St Pancras Way site. A new footbridge is being installed to connect public realm areas at 102 Camley Street and Granary Street. The bridge will be installed in three stages over a two week period. Following completion of the abutments to either side of the channel outside of the stoppage period, two approach ramps will be lifted into place where they will temporarily be cantilevered over the canal. The central span will then be lowered into place and secured to complete the deck. The three stages of installation will require navigation closure for the safety of canal users. This is the last of the 3 weekend closures. | Yes | 2025-02-15T08:00:00+00:00 | 2025-02-16T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28743-100m-east-of-bridge-31-oblique-bridge-near-st-pancras
28177 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Lock 2 East, Coal Wharf lock, Huddersfield | A stoppage is required to allow Lock gate replacement and lock chamber repairs. | No | 2025-02-17T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28177-lock-2-east-coal-wharf-lock-huddersfield
28214 | Navigation Closure | Wales & South West | Kennet & Avon Canal | Lock 80, Copse, Kintbury | A stoppage is required to carry out repair and refurbishment works to the top and bottom lock gates. | No | 2025-02-17T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28214-lock-80-copse-kintbury
28234 | Navigation Closure | London & South East | Grand Union Canal | Lock 31, Horton Lock, near Slapton | A stoppage is required to carry out replacement of the top and bottom lock gates. We are also repairing the brickwork in the lock chamber. | No | 2025-02-17T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28234-lock-31-horton-lock-near-slapton
28763 | Navigation Closure | London & South East | Waterworks River | Bridgewater Road Bridge | A stoppage is needed so the existing Bridgewater Road Bridge can be demolished and new bridge structure installed at same location. | Yes | 2025-02-17T08:00:00+00:00 | 2025-03-09T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28763-bridgewater-road-bridge
29098 | Navigation Closure | West Midlands | Worcester & Birmingham Canal. | Lock 28, Stoke Prior, Near Bromsgrove | A navigation and towpath closure are required for bottom end gate replacements and a full lock ladder rebuild. The whole flight will be closed for safety reasons. | Yes | 2025-02-17T08:00:00+00:00 | 2025-03-14T18:00:00+00:00 | https://canalrivertrust.org.uk/notices/29098-lock-28-stoke-prior-near-bromsgrove
28148 | Navigation Closure | North West | Huddersfield Narrow Canal | Lock 12 West, Mossley | A stoppage is required for repairs to the failing towpath wall. We will also be doing repairs to the offside embankments. | No | 2025-02-17T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28148-lock-12-west-mossley
29090 | Navigation Closure | London & South East | Regent's Canal | Islington Tunnel | A navigational closure is required to enable tunnel barrel inspections. Parts of this work may take place at nighttime as well as during the day. If floating buoys are across the entrance to the tunnel within the water, then the tunnel is closed, and no passage is possible. | No | 2025-02-24T16:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/29090-islington-tunnel
28193 | Navigation Closure | Yorkshire & North East | Huddersfield Narrow Canal | Lock 32 East, by Sparth reservoir | A stoppage is required for Lock gate heel timber repairs. | No | 2025-03-03T08:00:00+00:00 | 2025-03-14T16:00:00+00:00 | https://canalrivertrust.org.uk/notices/28193-lock-32-east-by-sparth-reservoir